## Inspection Info
Summary of Code Inspections Carried Out
Project | Inspection ID | Start Date | Completion Date | Work Product | Author | Number.of.Inspectors | Product.Appraisal | Size.Planned, LOC | Size.Actual, LOC | Percent.Inspected | Effort.per.Defect (labor hours) | Defect.Density (defects/KLOC) | Rate.Preparation (LOC/hour) | Rate.Inspection (LOC/hour) | Effort.per.Unit.Size (labor hours/KLOC) | Rework.per.Defect (labor hours)
B | CODE-1 | 2001-01-03 | 2001-01-10 |  | Jill | 4 | conditional | 1175 | 834 | 70.9787 | 0.34028 | 86.3309 | 522.2222 | 370.6667 | 39.5683 | 0.53125
A | CODE-5 | 2000-11-15 | 2000-11-19 |  | Fred | 6 | accepted | 740 | 740 | 100 | 0.34884 | 116.2162 | 341.5385 | 370 | 55.4054 | 0.5
A | CODE-3 | 2000-10-04 | 2000-10-14 |  | Marvin | 5 | re-inspect | 458 | 458 | 100 | 1.2647 | 37.1179 | 218.0952 | 229 | 55.6769 | 0.23529
Averages | [5 empty] | 5 |  | 791 | 677.3333 | 90.3262 | 0.65127 | 79.8884 | 360.6186 | 323.2222 | 50.2169 | 0.42218

## Defects
Record of Defects for Each Inspection
|  | Extra |  | Wrong |  | Missing |  | Usability |  | Performance
Project | Inspection ID | Major | Minor | Major | Minor | Major | Minor | Major | Minor | Major | Minor | Defects.Found.Major | Defects.Found.Minor | Defects.Found.Total | Percent.Majors | Defects.Corrected.Major | Defects.Corrected.Minor | Defects.Corrected.Total
B | CODE-1 | 4 | 18 | 6 | 12 | 4 | 18 | 2 | 4 | 1 | 3 | 17 | 55 | 72 | 23.6111 | 12 | 4 | 16
A | CODE-5 | 7 | 14 | 13 | 27 | 8 | 11 | 0 | 1 | 0 | 5 | 28 | 58 | 86 | 32.5581 | 17 | 5 | 22
A | CODE-3 | 3 | 3 | 3 | 6 | 1 | 1 | 0 | 0 | 0 | 0 | 7 | 10 | 17 | 41.1765 | 7 | 10 | 17
Averages |  | 4.6667 | 11.6667 | 7.3333 | 15 | 4.3333 | 10 | 0.66667 | 1.6667 | 0.33333 | 2.6667 | 17.3333 | 41 | 58.3333 | 32.4486 | 12 | 6.3333 | 18.3333

## Effort
Record of Effort for Each Inspection
Project | Inspection ID | Time.Meeting, hours | Effort.Planning (labor hours) | Effort.Overview (labor hours) | Effort.Preparation (labor hours) | Effort.Meeting (labor hours) | Effort.Rework (labor hours) | Effort.Inspection (labor hours)
B | CODE-1 | 2.25 | 0.5 | 6 | 9 | 9 | 8.5 | 33
A | CODE-5 | 2 | 1 | 4 | 13 | 12 | 11 | 41
A | CODE-3 | 2 | 1 | 0 | 10.5 | 10 | 4 | 25.5
Averages |  | 2.0833 | 0.83333 | 3.3333 | 10.8333 | 10.3333 | 7.8333 | 33.1667

## Help Info
This spreadsheet illustrates the use of the code inspection tracking spreadsheet described in
Chapter 9 of Peer Reviews in Software: A Practical Guide by Karl E. Wiegers (Addison-Wesley, 2001).
There are three worksheets in the spreadsheet:
Inspection Info - | contains summary info and statistics about each inspection, one inspection per row
Effort - | contains cells to enter the total hours spent on various parts of the inspection event
Defects - | contains cells to enter the total number of defects found in each inspection,
separated by severity (major and minor) within type of defect or issue
Enter the data for your first inspection into Row 5 in each of the worksheets.
To create rows to hold data for a new inspection, run the InsertRows macro (Tools/Macro menu).
Each time you run this macro, it will insert one new row at the top of each of the three worksheets in Row 5
and insert the necessary formulas.